## Slide 1: RISK MANAGEMENT PRESENTATION SUMMER CAMP IN MAINE
Group 3
Aslanbek Xembayev
Rahul Iyer
Erh-Hsiang Huang
Qian Liang
Zichao Zhou

## Slide 2: Overview
Build camper’s social skills through on-camp and outdoor activities.
Activities include:
Hiking
Fishing
Camp-fire
Exploration of Maine’s forest
Project Budget - $499,100
Number of campers - 300 (estimated)
Project Schedule - 12 Weeks
  Initiation-1 week
  Planning-5 weeks
  Execution-4 weeks
  Closure-1 week
Number of Employees - 25 members, including 5 security staff and 5 doctors.
Notes: Our team is concerned that kids are spending too much time with electronic devices and are not experiencing nature in its true form. We want to teach kids how to make friends by building social skills in a proper way. Therefore, we have decided to set up a summer camp that can teach children useful skills such as hiking, camping, fishing, as well as permit kids embrace mother nature in a electronic free environment. The camp will be set up in Maine, home to a lot of forests.
Reference: Camp Caribou. (n.d.). Unforgettable summers since 1922. Retrieved from: http://www.campcaribou.com

## Slide 3: Key Components
Risk Identification: Cause, Condition, Consequence, Category, Risk Owner, Trigger
Risk Analysis: Probability, Impact, EMV Cost & EMV Duration
Risk Evaluation: Classification of risks based on priority, rank
Risk Response: Response Method(Mitigate/Avoid/Transfer/Accept), Details of Response, Integration with project plan, Cost of Response, Secondary risk and its response
Risk Monitoring and Controlling- Review Risk, Current Status of Risk

## Slide 4: Risk Identification
Approaches: 1. Group Brainstorming
2. Development of 5 risks individually and mutually approved by group
STRENGTHS | WEAKNESSES
Share more ideas | Weak results if implemented online
Combine advantageous ideas | Logically inconsistent ideas
Test ideas | Focus is more on number of ideas compared to quality of those ideas.
Instant feedback | 
OPPORTUNITIES | THREATS
Better Communication | Possibility of vague ideas
Ease in assignment of responsibilities | Conflicts- due to different opinions
Individual perspective | 
Notes: Our team used Brainstorming technique for risk identification. Each team member came up with at least 5 risks associated with the summer camp project.

## Slide 5: Risk Prioritization
Risks were prioritized from:
Risk probability (calculated on 5)
Impact of the risk (calculated on 5)
Calculation of Risk Rank
Justification for the approach:
Easy to comprehend
Parameters can be easily estimated
Gives a straightforward result
Reliable numerical data
Value | 1-2 | 3 | 4-5
Likeliness/Severity | Low | Medium | High
Risk Rank | Response
2-4 | Response Not Required
5-7 | Monitor
8-10 | Response Required
Notes: Risk Rank = Probability + Impact
Our approach of Risk Rank addresses risk prioritization numerically and in a straightforward way. Based on Risk Rank, we have the capability to make a decision on how to respond to risks as per the table.

## Slide 6: Contingency Reserve
Contingency reserve - $33,000.
Reasons behind this amount:
Usually range for contingency varies between 5% - 10% of project budget. Contingency is taken as 6.7% for the summer camp.
Serves as additional financial insurance on top of budget. Budget already includes funds to cover risk responses.
Sufficient for contingency funds for responses to secondary risks (if necessary)
Notes: Our budget is limited to $499,100, where $466,100 is sum of all expenses (such as camp rent, salary for employees, food, etc.) that are necessities.
This amount serves as additional financial insurance on top of budget, and it’s sufficient as all necessary expenses are calculated with consideration of identified risks and response strategies. For example, to avoid risk (#2) of hiring employees with criminal history, we reserved $10k for recruitment agency that will screen and run background checks of each job candidate.
Contingency reserve will be used for unexpected (unlikely) events that we didn’t plan for such as a response for secondary risks. For example, in case of bad weather (risk #5), we implemented 1st response, and even though there is a low probability of storm persisting, our secondary response is to organize nice dinner in canteen. Contingency reserve can cover this expense.
We planned to have 5% - 10% reserved as contingency reserve. $33,000 is 6.7% of total project budget.

## Slide 7: Risk Response development strategy
STEPS:
Based on Risk Rank (slide #5), decide whether a response is necessary or not
Classify risks - negative or positive
If negative, choose a strategy: AVOID/TRANSFER/MITIGATE/ACCEPT
If positive, choose a strategy: EXPLOIT/SHARE/ENHANCE/ACCEPT
Develop actual risk response plan
Identify secondary risk
Analyze secondary risk (Probability & Impact)
Response plan for secondary risk
Monitor and control risks
Notes: Based on chosen strategy, make an actual plan of action (write response, integrate with project plan, add cost of response, reassess risk in terms probability and impact, add contingency plan

## Slide 8: Risk Control Strategy: Monitoring
Discuss potential risks/threats as a part of everyday team meetings
Update risk status regularly
Report updated risk status to key stakeholders
Use contingency reserve (if necessary)
Different teams should report to their team leaders on a daily basis

## Slide 9: Value of Risk Management
l
To-do list:
Continuous Monitoring of risks
Updating Risk Register regularly
Documentation of experiences in lessons learned document
 | Before | After
Stakeholders communications | Unclear stakeholder requirements | Better communication with stakeholders
Contingency Planning | Lack of contingency reserve | Development of a contingency plan An estimated Contingency budget
Risk Prioritization | All risks are treated equally | Risk prioritization
Risk response planning | Costs associated with risk response and secondary responses are not identified | Effective risk response strategies Integration with project plan
Risk monitoring and control | Improvisation Reactive approach | Plan-of-action Better preparedness Pro-active approach
Notes: The project team made the total contingency request $33,000 and EVM technique provides a formula for determining the right amount of budget to apply to the risk contingency budget.
Classify all the risk and develop response strategies to ensure the responses are effective for the risk and its impact. Integrate response strategies into project plans and analyze secondary risks.
Since risk management is an iterative process that begins in the early phases of a project and is conducted throughout the project life cycle, project team should:
Review overall risk management documentations and continuously monitor identified risks
Document results of the monitor and control risk processes to provide concrete data to the lessons learned document

## Slide 10: References
Howard, J. (2017). Kids under 9 spend more than 2 hours a day on screens, report shows. Retrieved from: https://www.cnn.com/2017/10/19/health/children-smartphone-tablet-use-report/index.html
Camp Caribou. (n.d.). Unforgettable summers since 1922. Retrieved from: http://www.campcaribou.com