## Summary Sheet
Group Number: | 3
Group Members | Aslanbek Xembayev
Rahul Iyer
Erh-Hsiang Huang (ERIC)
Qian Liang (Monica)
Zichao Zhou
Cost Breakdown
Camp rent | 200000
Insurance(USD 250 / camper) | 25000
Bus to national park | 1500
Entry tickets to the national park | 1000
Entry tickets for whale watching | 2000
Boat rental | 1200
Consulting fees from camp caribou | 5000
Salary for team members (20 members, 4K/month for each member) | 80000
Marketing and advertising costs | 10000
Employee training cost | 20000
Contingency | 33000
Food ($35/child/day) | 100000
Water filter for swimming pool | 400
Renovation | 10000
Recruitment Agency | 10000
Total Cost | 499100
Brainstorming Approach
Our team used Brainstoring technique for risk identification. Each team member came up with at least 5 risks assocaited with summer camp project. Our team met twice to discuss possible risks.
Note: | Each team member should develop 4 risk items
Name | Risks | Number | Consequence
Aslanbek Xembayev | Death - drowning in swimming pool | 1 | Will shut down summer camp
| Inappropriate counselors' behavior towards children | 2 | Crimes towards campers of all types can shut down which summer camp program
| Poor medical preparedness | 3 | Kids don't feel well and have to go to hospital for medical assistance
| Late cancelation | 4 | Certain plans, cotingency plans and salary payments are at risk of not being paid on time
| Storm (Bad weather) | 5 | Children won't be able to go hiking, camping, whale watching or go on a trip to National Park
Erh-Hsiang Huang (ERIC) | A highly contagious Influenza goes around each kid | 6 | children will need to be isolated and the camp will shut down
| Lost valuable items, such as electronic devices, custody by supervisors | 7 | parents will request compensation, causing extra cost
| Staff misappropriate the funds | 8 | camp loses all the money and shut down
| Online registration doesn’t work | 9 | people can't register the camp
| Regulatory and legislative changes | 10 | violate the law
Rahul | Insufficient security or supervision on kids | 11 | Kids are kidnapped during outdoor trips
| Less control over campfire | 12 | Campers may receive severe burns on their body that could lead to death
| Supervisor's careless attitude or absence of mind | 13 | Missing kids, bad reputation for the organization
| Lack of registered campers | 14 | Project's budget would be constrained
| Unsafe wild-environment with poisonous snakes, insects and spiders | 15 | Children would require medical attention if bit; severe damage to health or death is also possible.
Qian Liang （Monica） | Children do not obey policies | 16 | Fighting may cause injury
| Supplier risks | 17 | Camps may get complaints from children and parents
| Conflicts between co-workers | 18 | Negative impact on teaching quality
| Camp caribou senior leadership loss | 19 | Poor performance of senior management
| Infrastructure risks | 20 | Some skill training can not be achieved and bring a bad reputation to the camp
Zichao | Funds are not available on time | 21 | leading the beginning date of summer campus have to be postponed
| Staff Absence | 22 | children may not get the good careful of care
| Spending money in the wrong way | 23 | we may not can provide a wonderful service
| Food contractor can’t deliver food produce on time | 24 | children and their parents will be angry
| The bus trip has an accident on its way to the national park | 25 | we have to shut down the summer camp

## Risk Identification
| Risk Identification | [6 empty] | Risk Analysis | [7 empty] | Risk Response Plan | [9 empty] | Risk Monitoring and Controlling
Name | Risk Number | Risk Statement |  |  |  | Risk Owner | Trigger | Qualitative Analysis |  |  |  | Quantitative Analysis |  | Risk Rank (1 - low, 10 - high) | Risk Action | Risk Response | Detail of Response | Integration with Project Plan | Cost of Response | Reassessment of Risk |  | Contingency Plan | Secondary Risk | Secondary Risk Analysis | Secondary Risk Response | Risk Status
|  | Cause | Condition | Consequence | Category |  |  | Probability (1-low to 5-high) | Reasoning | Impact (1-low to 5-high) | Explanation | EMV-Cost | EMV-Duration | 2 to 4-Response Not Required, 5 to 7-Monitor, 8 to 10-Response Required | [5 empty] | Probability | Impact |  | Risk introduced based on Risk Response
Death | 1 | Due to poor supervision and lack of swimming training | a camper can be drown in the pool | Which will close camp down | Campers | Activities Director | Absence of lifeguard | 1 | No substitute for adult lifeguard in case he/she is missing | 5 | Death of a camper kid automatically means other parents will take their kids away from camp, investigation starts and camp has to be closed for it. | Probability = 20% Impact = $800000 EMV = $160000 | Probability = 20% Impact = 31 days EMV Duration = 6.2 days | 6 | Response required | Avoid | 1) Make pool height entrance limit, 2) swim test before letting into pool, 3) life jacket for those who fail swim test, 4) have lifeguard in place | Train employees to know these regulations, hire lifeguard and make sure Camp caribou has life jackets in stock | 4000 | 1 | 3 | 1) Lifeguard, 2) Warning signs, 3) Life jackets | Lifeguard is not next to pool | Probability - 1, Impact - 4 | When there are pool activities, instruct all staff to report immediately if lifeguard is not in place. Also, while lifeguard is missing, be present next to pool and prepare to save children if someone starts to drown.
Inappropriate counselors' behavior | 2 | Due to poor screening during hiring | We may hire wrong people to work with kids | Crimes towards campers of all types can shut down which summer camp program | Staff | Project Manager | Complaints from campers | 2 | People with criminal past (sex offender) were not gone through screening prior being hired | 5 | Crime against a camper will lead to shutting down whole summer camp program and investigation | Probability = 40% Impact = $800000 EMV = $320000 | Probability = 40% Impact = 31 days EMV Duration = 12.4 days | 7 | Response required | Avoid | Screen every job applicant for criminal / inappropriate history | Hire recruitment agency to avoid this risk | 10000 | 1 | 3 | recruitment agency will have tools to run screen checks | Screening doesn't help and inappropriate counselors can still be hired | Probability - 1, Impact - 3 | Counselors work in groups of two, so they watch each other
Poor medical preparedness | 3 | Due to absence of doctors | We might not be able to offer medical help on site when needed | Kids don't feel well and have to go to hospital for medical assistance | Campers | Project Manager | Camper gets sick | 4 | Headaches, stomach ache, or a minor injury can become worse and affect camper enjoy camp activities | 3 | Campers who get sick can't participate in program's activities | Probability = 80% Impact = $24000 EMV = $19200 | Probability = 80% Impact = 5 days EMV Duration = 4 days | 7 | Response required | Mitigate | Have a health center | Hire a doctor | 4000 | 1 | 2 | Doctor will have medication and license to treat patient children | Child doesn't have health insurance | Probability - 1, Impact - 3 | Not allow a child to be signed up for the summer camp program unless he/she has an insurance. Document it.
Late cancelation | 4 | Due to parents' own reasons | We may have not enough money to pay for expenses at the end | Certain plans, contingency plans and salary payments are at risk of not being paid on time | Staff | Project Manager | Parents cancel summer camp and ask for 3 days before start date | 1 | Parents' can have their own reasons why they decide to cancel | 3 | Some might decide to cancel last minute | Probability = 20% Impact $24000 EMV = $4800 | Probability = 20% Impact = 5 days EMV Duration = 4 days | 4 | Response required
Storm (Bad Weather) | 5 | Due to bad weather such as storm | Most activities outdoor activities would have to be canceled | Children won't be able to go hiking, camping, whale watching or go on a trip to National Park | Children and staff | Director of Activities | Bad Weather occurs | 3 | With bad weather some activities will have safety hazards such as whale watching on a boat or slippery conditions during hiking/camping | 4 | Bad weather (storm) is worse than forecasted | Probability = 60% Impact = $10700 EMV = $6420 | Probability = 60% Impact 7 days EMV Duration = 4.2 days | 7 | Response required | Accept | Replace outdoor activities and trips to indoor activities | Plan indoor activities in advance as a replacement for outdoor activities and trips | 1000 | 1 | 1 | Have enough board games, playing soccer, volleyball balls, etc. | Bad weather (storm) lasts longer than expected | Probability - 1, Impact - 1 | Organize nice dinner in camp's canteen
Disease | 6 | Due to a lack of health care and periodic inspection | A highly contagious Influenza goes around each kid | children will need to be isolated and the camp will shut down | Children and staff | Activities Director | lack of health care | 4 | Outdoor activities and weather changing will easily cause disease. Children live together in the same space, causing virus infects to each other. | 4 | Multiple sick campers will lead to schedule delay, medical take care, and crash the foundation of trust among stakeholders. | Probability=80% Impact = $100,000 EMV-Cost = $80,000 | Probability=80% Impact = 2 days EMV-Duration = 1.6 days | 8 | response required | Mitigate | Prepare medical assistance and ask for health record from campers | Ask all campers to deliver there health and immunization record while they register. Allow only campers who ever had a vaccination. Set up a health center with nursing staffs after the camp start. | 5000 | 2 | 3 | Health center should open 24 hours a day and have at least one ambulance stand by. Transfer risk to health insurance company. | Nursing staffs might not as much professional as regular doctors and might not have sufficient medical equipment's to handle severe disease. | Probability- 1, Impact-3 | Recruit nursing staffs with at least 7 years experiences.
Theft | 7 | Due to a lack of supervision | Lost valuable items, such as electronic devices, custody by supervisors | parents will request compensation, causing extra cost | Staff | Project Manager | lack of supervision | 2 | All the valuable items will be Comprehensive monitored by staff | 2 | Compensate the lost for campers | Probability = 40% Impact = $3,000 EMV-Cost = $1,200 | N/A | 4 | response required | Avoid/ Militate | Set up monitors | Register all valuable items and put into safe case, with 24 hours supervised by security company and monitors. | 2000 | 1 | 1 | Transfer responsibilities to security company. | Power black out/ Monitors malfunction. | Probability-1, Impact-1 | Put at least one staff to secure the safe box.
Misapproprite fund | 8 | Due to lack of a strict management | Staff misappropriate the funds | camp loses all the money and shut down | Staff | Project Manager | lack of strict prossess | 1 | The fund will be carefully controled by mutiple project managers | 5 | Lost all the money, causing the camp shot down | Probability = 20% Impact = $500,000 EMV-Cost = $100,000 | Probability=20% Impact = 60 days EMV-Duration = 12 days | 6 | response required | Avoid | Background check on all staffs and set up billing procedures. | Ask all staffs to sign legal contracts and have background check before recruitment. Distribute the funds on several accounts. Have several procedures when moving funds. | 1000 | 1 | 2 | Have a legal consultant and accountant | Conflict between cross department due to multiple procedures. | Probability-1, Impact-2 | Set up human resoureces to solve problems
System Malfuction | 9 | A system break down | Online registration doesn’t work | people can't register the camp | Staff | Project Manager | lack of maintenace of server | 1 | A team will response on taking care of server and make sure it work well | 4 | Campers can't find the website to register | Probability = 20% Impact = $10,000 EMV-Cost = $1,000 | Probability=20% Impact = 7 days EMV-Duration = 1.4 days | 5 | response required | Avoid/ Mitigate | Create a second link and increase the registration time | Set up a second link for customers and enhance the server. Have an IT team to supervise the system. Moreover, extent the registration time for customers so that they can sigh up earlier. | 2000 | 1 | 2 | Create a customer service to answer the phone call who have a problem on registration. | Customers lose the interest in dead website | Probability-1, Impact-3 | To create another link and contact information on Facebook, Instagram,and Twetter.
Legislation change | 10 | Due to a change in low | Regulatory and legislative changes | violate the law | All project teamates | Project Manager | Doesn't notice the change of law | 1 | All the project managements should study all the legislations and consult with lawers before we start operation. | 5 | Will delay the scheldue and could be penalized a fine from legal forces. | Probability = 20% Impact = $100,000 EMV-Cost = $20,000 | Probability=20% Impact = 14 days EMV-Duration = 2.8 days | 6 | response required | Avoid | Legal consultant | Check out with legal consultants and lawers all the time and make sure all the activities would not violate the law. | 5000 | 1 | 2 | Set up backup plans in all activities in case the first one have legislation problems. | Too many activities plan confuse all the staffs, causing them making mistake | Probability-1, Impact-1 | Have a staff meeting to explan the schedule before all activities start.
Infrastructure risks | 11 | Due to lack of maintenance/storm damage | Inconvenience to camp everyday routine / Disruption to camp learning programs | Some skill training can not be achieved /Which will give a bad ruputation to the camp |  | Coaches/Project manager | Lack of lack of maintenance | 3 | Staff should ensure the normal use of camp area facilities , but bad weather or some human-made damage can cause infrastructure issues | 3 | It will affect the quality of teaching, and any facilities failure can also cause safety problems which may make extra cost | Probability= 60% Impact=$50,000 EMV-Cost =$30,000 | Probability= 60% Impact= 3 days EMV-Duration =1.8 days | 6 | Response required | Mitigate | Arrange camp staff to carry out routine maintenance to ensure all malfunctional facilities can be repaired or replaceed in time | Damage caused by campers who intentionally damage the infrastructure may increase our contingency fund | 2000 | 2 | 2 | Set up alternative courses or activities in case the infrastructure can not be use in specific coures | No enough Qualified coach for back-up courses | Probability-1, Impact-3 | Adjust the coach's schedule due to the alternative activities or second someone from other camp
Management risk | 12 | Due to lack of experiences of summer camp project | lead to highly turn-over or lack of collaboration | Poor performance of senior management | All project team members | Project manager | Lack of experience | 2 | Since this is our first summer camp project,the project team may lack enough information and experience | 4 | Lack of relevant experience may lead to poor performance of project management, which may have a negative impact on kids and staff daily routine. Serious can affect the cost or schedule overruns; even can cause project failures. | "Probability= 40% Impact = $1,000 EMV-Cost = $400 | Probability= 40% Impact= 1 days EMV-Duration =0.4 days | 6 | Response required | Mitigate/Avoid | Rigorous appointment procedures | Make a strict appointment process rules. The management team should review candidates' professional background and managerial ability when selecting | 3000 | 1 | 3 | Try headhunter to help find qualified candidates | The costs of money and time for recruiting right person will be increased | Probability-2, Impact-2 | Project management team vote to elect appropriate member with management capacity
Conflicts between co-workers | 13 | Due to personality diversity and Communications Factors | Conflicts between colleagues | Negative impact on teaching quality | Staff | Project Manager | Problems of communication | 1 | Staff we hired are qualified and with great communication skill | 2 | Conflicts may cause work inefficiency and may slow down project or teaching progress | Probability= 20% Impact=$10,000 EMV-Cost =$2,000 | N/A | 3 | Response required | Miligate | Provide communicaiton training | All staff will professional communication training before camp start，And they will conduct performance evaluation for each other | 500 | 1 | 2 | Conduct Performance evaluations everyweek among co-workers and Resolve potential communication problems | Some evaluations for co-workers may not be objective enough to reflect their performance | Probability-2, Impact-2 | Hire new staff
Supplier risks | 14 | Due to the product or service provided by suppliers may avialible or of poor quality | Children will have negative experiece from low quality services or facility | Camps may get complaints from children and parents |  | Project manager |  | 2 | The project team have done a sufficient brand survey when selecting suppliers and alternative suppliers always considered | 3 | Poor product or services offered by suppliers may damage the camp's reputation, and the bad experience may cause complain or even request a refund | Probability= 40% Impact=$180,000 EMV-Cost =$72,000 | Probability= 40% Impact= 6 days EMV-Duration = 2.4 days | 5 | Response required | Avoid | Carefully screen qualified suppliers and Creating a supply base to ensure that once the current supplier is not available or unqualified, the project team can have an alternative qualified supplier. | Add the task of creating a supply base to WBS and it may impact the project costs and schedule estimates | 2500 | 2 | 3 | Hire legal consultants to clearly define your rights in specific event when sign up with suppliers | The alternative Supplier may also unavailable or reflect to make a contract due to many of risk transfer clauses | Probability-1, Impact-2 | Doing more supply search and Contact same kind of suppliers in the supply base.
Children do not obey policies | 15 | Due to a lack of supervision | Children may break the rules of the camp like fighting with each other | Which will cause injury | Staff | Project manager | Staff do not pay enough attention to children | 3 | Staff paid enough attention to every kid, and everyone in summer camp got the clear understanding of the camp policy, However, due to the elementary and middle school kids may lack the self-control. | 3 | It will cause safety problems.Serious accidents or personal injuries will result in huge compensation or the camp would force to close down | Probability= 60% Impact=$85,000 EMV-Cost =$51,000 | N/A | 6 | Response required | Mitigate | Our camp has a 9:1 student-to-staff ratio to ensure every child can be well cared for. | Increase activities and courses for children to understand each other and to help them become closer. | 800 | 2 | 2 | The camp will hire child experts to help children solve emotional problems | Too many kids lead to Insufficient staff for supervising | Probability-2, Impact-3 | Post job ads on social media or nearby communities
Safety endangered | 16 | Insufficient security | Some campers may not be accounted | Children missing | Management | Camp Caribou’s security manager | Inaccurate estimation of Human Resources | 3 | The location of the camp is isolated from the city, making it a little unsafe especially for children. Cases of kidnapping have been reported several times over the past few years. At the same time, we have installed CCTVs to keep a track of children. Therefore, the risk has a moderate probability of occurrence | 4 | Missing children cases on camp-premises reflects poor preparedness and lack of professionalism on the management's side. | Risk Probability=60%. Impact=$4000 EVM(Cost)=$2400 | N/a | 7 | Response required | Mitigate | Hire more security guards | Recruit more security guards from reliable recruiting agency. Locate them at all possible exits. Instruct them to conduct an ID check on campers and supervisors to ensure no one unknown enters | 5000 | 2 | 3 | CCTV installation with multiple monitors and supervisors observing them, effective communication through radio covering the entire camp | Indivduals posing as campers or supervisors can create fake IDs and maybe granted access to the camp. | Probability-1, Impact-3 | Changing the entry setup that makes use of the camper's registered account details including a unique username and password.
Fire Hazard | 17 | Less control over campfire | Children may have severe burns and possibly die | Parents would sue the organization | Management | Camp Organizer | No safety precautions | 1 | According to statistical data, campfire accidents occur rarely but we have decided to consider at as a minor risk factor | 4 | Death of a child is a very serious threat. The PM maybe held responsible and jailed for it while the organizers may have to provide parents with a compensation | Probability=20% Impact=$10000 EVM(Cost)=$2000 | N/a | 5 | Response required | Avoid | Maintain distance from fire | Draw a boundary circle at a safe distance from the campfire. Instruct supervisors and campers to maintain their distance and not cross the boundary for safety reasons. | N/A | 2 | 2 | Transfer the risk to a professional organizer who would conduct the entire campfire activity under his team's supervision. | Disobedient campers may cross the boundary | Probability-1, Impact-1 | Maintain a ratio of 1:1 between children and supervisors and instruct supervisors to be more careful at such events. Keep fire extinguishers and first aid kit handy and medical support within reach.
Few campers | 18 | Inadequate number of registrations | Fewer children and lesser money involved in the project | Budget would be constrained | Organizational | Project Manager | Bad choice of advertisement channels | 3 | Lack of advertisement campaigns and awareness among families may or may not have an influence over the number of registrations | 3 | Many changes would need to be incorporated in the planning phase like meals, trips, vehicles to meet the reduced budget with very little time for accomplishment | Risk Probability = 60% Impact = $10000 EVM(Cost) = $6000 | Risk Probability=60% Impact=10 days. EMV(Duration)=6 days | 6 | Response required | Mitigate | Social media awareness | Start a twitter page prior to the commencement with #Camp_Caribou#2018 | 200 | 2 | 3 | Provide annual membership at a much more reasonable price. | Parents do not follow social media websites and are not interested to participate in such activities | Probability-1, Impact-2 | Availability of live feed that would help parents track their children's progress through the camp and their current location
Safety threatened | 19 | Supervisor’s careless attitude | Children are kidnapped during outdoor trips | Bad reputation for the organization | Management | Hiring Manager | No background check for professional experience | 1 | We have hired experienced recruiters to recruit suitable supervisors for the camp and given special instructions to run a background-check prior to employment | 4 | The reputation of the camp will be at stake if such an incident occurs because of one individual's mistake. Families will refrain from sending their children to a camp that has an history of kidanapping cases. | Risk Probability=20% Impact=$16000 EVM=$3200 | Risk Probability=60%, Impact=5 days. EMV(Duration)=3 days | 5 | Response not required | Transfer | Use existing camp's supervisors | Each supervisor must be alloted with 2 to 3 campers. The supervisor must remain with the campers at all times for outdoor activities as well as activities within the camp. | 2000 | 1 | 1 | A tracking device with a powerful range must be placed on each camper's shoe that would help to track the camper immediately. An alarm would be triggered if the camper goes beyond a certain distance and supervisors would be alerted too.
Wild environment | 20 | Poisonous snakes, insects, spiders | Children could be bitten | Severe damage/Death | External | Forest safety Department | Weak fencing and protection measures | 4 | The camp is not in close proximity to poisonous snakes, insects or spiders. There is a very low probability that they may attack the campers as they are not immediately | 4 | Such an event has the potential to shut down the camp forever because the Government shall not permit the operation of any camp threatening an individual's life. | Probability=80% Impact=$15000 EVM(Cost)=$12000 | N/a | 8 | Response required urgently | Mitigate | Medical assistance | Doctors must be present at all times with the campers with medication and antidotes | 2500 | 2 | 3 | Order customized clothes tailor-made for each camper that covers the entire body including extremities. The material should prevent the penetration of the snake bite. | The doctors may be bitten too.In such situation, the safety of both campers and doctors are endangered | Probability- 1, Impact-3 | Reduce the number of activities that involve close proximity to snake habitat.
Short of Money | 21 | Funds are not in place timely | the instruction will not be complete and have not engouh money for rental | leading the beginning date of summer campus have to be postponed | All project teamates | Project Manager | the finance manager does not make a good deal with soponsers | 1 | we can not do much more if we are lacking of money | 4 | we must done the negotiateion witht sponsors before the preparetion | Probability = 10% Impact = $200,000 EMV = $20,000 | n/a | 5 | Response required | Avoid | we will contact the sponosr immediately to urge the money. | Before the money into the account before the rental. | 1000 | 1 | 2 | Contact to sponsor | sponsor may not agree to invest | Probability - 1 Impact - 3 | Identify other sponsors instersted in the summer camp
Staff Absence | 22 | staff leave the working position | we might lack of labor sometimes | children may not get the good careful of care | Children | Project Manager | staff just left the work without mention | 2 | the intentional absense will make the team menber off guard | 2 | lack of labor will leading seiours problem such as accident. Because of childerne can not get an all-round care | Probability = 40% Impact = $4,000 EMV = $1,600 | Probability = 40% Impact =7 days EMV =1.4 days | 4 | Response required | Miligate | hiring two more staffs in the phase of prepration | register all staffs on the exact schedule before the opening, and reserve a free man to response the emergency | 3000 | 2 | 1 | increase the force of supervision, before everyone will be in the position
Sink Money | 23 | spending money in the wrong way | we may have the finaical gap | we may not can provide a wonderful service | All project teamates | Project Manager | we use too much money in unnecessary way | 2 | we do not have engough money to use in nessscary way | 3 | if we lack of money, the problem is coming serious. we may not have enough money to purchase engouh food and pay salary to staff | Probability = 20% Impact = $10,000 EMV = $20,000 | Probability = 20% Impact =20 days EMV =4 days | 5 | Response required | Avoid | Set up monitors, and increase the budget | 1 | 3000 | 2 | 1 | Transfer the responsibility to the monitor, and change the staff if it is necessary | inadequate supervision | Probability - 1 Impact - 2 | Change a professional supervisor who has the expericence with accounting
Food Deliver | 24 | Food contractor can’t deliver food produce on time | children will not recieve the food in time | children and their parents will be angry | Children and staffs | back office manager | lack of supervisor | 1 | Food contractor doesnt provide the food in time, then we may not have not engough food for lunch and dinner | 2 | children and their parents will not satisatfied with our campur and will not trust us again. In addition they might ask for refund. | Probability = 10% Impact = $100,000 EMV = $10,000 | Probability = 10% Impact =30 days EMV =3 days | 3 | Response required | Avoid/Miligate | communicate with the food supplier and supervise the food quality | During the phase of prepration, we will field visit the food supplier. To make sure that the supplier has ability to provide enougn food in time. In addition, we make some reserved money to cope with crisis | 8000 | 1 | 3 | Keep in touch with the food supplier, and supervision the food quality
Serious Traffic Accidents | 25 | The bus trip has an accident on its way to the national park | chilren and staffs maybe injured by accident | we have to shut down the summer camp | Children andstaffs | Project Manager and securities | fatigue driving | 1 | the traffic accident might cause serious injued such as death and fracture | 5 | the summer camp have to be close and we cannot make the profit | Probability = 10% Impact = $200,000 EMV = $20,000 | Probability = 10% Impact =30 days EMV =3 days | 6 | Response required | Transfer | pruchase the life insurance for every camper | if the serious traffic accident occured, contact to the insurance company and hospital immediately. In addition, let the familied know about what is going on | 10000 | 1 | 3 | being closely monitored with the transportation, and work toghter witht the security team | During the travel, driver is fatigue driving | Probability-1, Impact-2 | contact to the transporation company immediately, swtich another driver

## Risk Identification Method
Group Techniques for Risk Identification
Our team used Brainstorming technique for risk identification. Each team member came up with at least 5 risks assocaited with summer camp project. Our team met twice to discuss possible risks.
SWOT
STRENGTHS | WEAKNESSES
We felt free for sharing the idea of risk during the meeting | The brainstorming might not works well in the online meeting
We can encourage and complement with each other to share ideas | We might not always logically construct a good argument
Because there are no bad ideas in the brainstorming session, any interesting idea can be refined gradually. | Focus on quantity of ideas rather than quality
It produces visible results quickly
OPPORTUNITIES | THREATS
Get to know each other better | Some of ideas might go too far and become vague
Build responsibilities for everyone | Conflict might arise because of difference in points of view
Every team members have a chance to share his/her point of view